## 2019-2020
| January |  |  |  |  | February |  |  |  |  | March |  |  |  |  | April |  |  |  |  | May |  |  |  |  | June |  |  |  |  | July |  |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
WEEK | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
Summer Session TA Appointments
Approximate Dates:
2019-01-21 | List of courses with TA support for 2019S from Chris (list includes course, section, instructor, hours)
Jan-21-22 | Prepare 2019S Masterlist and create instructor listserve
2019-01-22 | Send list of courses to be added to 2019S TA application to Edmund
Jan 22-25 | Edmund prepares 2019S TA application
2019-01-28 | Instructors are emailed and advised to review online application to see # of assigned hours and review/revise posted Job Description for their course(s)
2019-02-08 | Deadline for instructors to update J/D and request change in hours
2019-02-14 | Deadline for Chris to revise assigned hours.
2019-02-15 | 2019S application goes live
2019-03-08 | Deadline to submit application
2019-03-11 | Instructors start selecting TA's
2019-03-29 | Last day for instructors to select 2019S TA's
2019-03-11 | Offers sent to students
2019-04-05 | Last day to send offers
Mar 18-Apr 12 | Process accepted offers
Mar 18-Apr 12 | Requests for union approval
Mar 18-Apr 18 | Email and confirm all new employees link employee ID with CWL
Apr 23-26 | Enter TA assignments in SISC, create TA listserve
2018-04-30 | Send final list of TA's to Union
Ongoing throughout this period:
-Change in courses (additions/deletions)
-Change in assigned hours
-Change in TA assignments
-Update TA Portal
May 1-June 15 | Distribute Health Rebate cheques to all 2018W Winter Session TA's
Winter Session TA Appointments
2018-02-11 | List of courses with TA support for 2018W from Chris (list includes course, section, instructor, hours)
Feb 11-22 | Prepare 2019S Masterlist and create instructor listserve
2019-02-25 | Send list of courses to be added to 2019W TA application to Edmund
Feb 25-Mar 8 | Edmund prepares 2019W TA application
2019-03-11 | Instructors are emailed and advised to review online application to see # of assigned hours and review/revise posted Job Description for their course(s)
2019-03-22 | Deadline for instructors to update J/D and request change in hours
2019-03-28 | Deadline for Chris to revise assigned hours.
2018-03-31 | 2019W application goes live
2018-04-30 | Deadline to submit application
May 1-7 | Prepare Preferred Status list and send to Union
2018-05-01 | Instructors start selecting TA's
2018-07-13 | Last day for instructors to select 2019S TA's
2018-05-01 | Offers sent to students
2018-07-26 | Last day to send offers
May 6-Aug 2 | Process accepted offers
May 6-Aug 2 | Requests for Union approval
May 6-Aug 23 | Email and confirm all new employees link employee ID with CWL
Aug 26-30 | Enter TA assignments in SISC, create TA listserve
2019-08-30 | Send final list of TA's to Union