## Gantt Chart Checklist
The Gantt Chart should include:
1. Task Names | Written in "action + description", active voice, and unique (non-repeating)
2. Responsible | Indicate who is responsible to complete the task
This is intended mostly for students (student's tasks). If you exclude SS/FS tasks, it's fine
3. Duration of Tasks | Shade the weeks you intend to work on the task
4. Dependencies | Using shading of weeks, you'll visualize which tasks can be done at the same time, and which tasks must be done one after another
5. Milestone dates | For major phases of the project, you can indicate an expected start date or completion date for that phase
Not all tasks will have milestone dates. You should only have 1-2 milestones per month

## Gantt Chart Template
Project Partner: | [Insert project partner name here]
Student: | [Your first and last name]
Date: | [Last modified date]
Graduating Project Gantt Chart
Task Name | Responsible | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20 | 2023-05-27 | 2023-06-03 | 2023-06-10 | 2023-06-17 | 2023-06-24 | 2023-07-01 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05 | 2023-08-12 | 2023-08-19 | 2023-08-26 | 2023-09-02 | Milestones | Comment
MFRE ACTIVITIES
Conduct start-up meeting/s | Student | bar: 2023-04-29 to 2023-05-13
Develop and submit project plan | Student | 2023-05-20: May 21 | Project Plan Complete (May 21)
Complete project progress check-in survey | Student | bar: 2023-06-03; 2023-07-01; 2023-07-29
Submit Gantt Chart | Student | 2023-06-03: Jun 6
Attend mid-stream assessment | Student | bar: 2023-06-10
Confirm final deliverables to MFRE | Student | bar: 2023-07-15
Email project deliverables to FS | Student | 2023-08-05: Aug 9
Submit 2-sentence summary and slides | Student | 2023-08-12: Aug 18
Present at Project Showcase event | Student | 2023-08-19: Aug 22 | Final Presentation Conducted (Aug 22)
Submit MFRE brief and supporting docs | Student | 2023-08-19: Aug 23
Email final Project Partner Deliverables to SS | Student | 2023-08-26: Aug 26-30
PROJECT PARTNER ACTIVITIES