## Gantt Chart Guidelines
The Gantt Chart should include:
1. Task Names | Written in "action + description", active voice, and unique (non-repeating). Organize your Tasks (either by deliverable, by phase, by method, or other).
2. Responsible | Indicate who is responsible to complete the task.
If working in a Team, indicate who is responsible for specific tasks.
This is intended mostly for students (student's tasks). If you exclude SS/FS tasks, it's fine.
3. Duration of Tasks | Shade the weeks you intend to work on the task (General guideline: task breakdown should be between 1-2 weeks).
4. Dependencies | Using shading of weeks, you'll visualize which tasks can be done at the same time, and which tasks must be done one after another.
5. Milestone dates | For major phases of the project, you can indicate an expected start date or completion date for that phase.
Not all tasks will have milestone dates. You should only have 1-2 milestones per month.

## Gantt Chart Template
Project Partner: | [Insert project partner name here]
Student: | [Your first and last name]
Date: | [Last modified date]
Graduating Project Gantt Chart
Task Name | Responsible | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | Milestones | Comment
MFRE ACTIVITIES
Meet with FS | FS | bar: 2025-04-28
Conduct start-up meeting/s | Student | bar: 2025-05-05 to 2025-05-12
Develop and submit project plan | Student | 2025-05-19: May 21 | Project Plan Complete (May 21)
Complete project progress check-in survey | Student | bar: 2025-06-02; 2025-06-30; 2025-08-04
Submit Gantt Chart | Student | 2025-06-02: Jun 6
Attend mid-stream assessment | Student | bar: 2025-06-09
Confirm final deliverables to MFRE | Student | bar: 2025-07-14
Email project deliverables to FS | Student | bar: 2025-08-04
Upload 2-sentence summary | Student | bar: 2025-08-04
Upload Project Showcase slides | Student | bar: 2025-08-11
Present at Project Showcase event | Student | 2025-08-11: Aug 14 | Project Showcase (Aug 14)
Submit MFRE brief and supporting docs | Student | bar: 2025-08-18
Email final Project Partner Deliverables to SS | Student | bar: 2025-08-18 to 2025-08-25
PROJECT PARTNER ACTIVITIES